## O-Feature-Inventory
O-Feature-Inventory — Master View
# | Feature_ID | Category | Feature_Name | Phase | Priority | Effort | Status | Owner
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69

## O-Phase-Summary
O-Phase-Summary — Rollup by Phase
Phase | Total | Not Started | In Progress | In Review | Done | Deferred | % Complete | Effort Points
MVP
Phase 2
Phase 3
Phase 4
TOTAL

## C-Feature-Calcs
C-Feature-Calcs — Derived Metrics
Feature_ID | Phase | Effort | Effort_Pts | Status | Is_Done | Is_In_Progress

## I-Features
I-Features — Master Feature List (Inputs)
Feature_ID | Category | Feature_Name | User_Story | Acceptance_Criteria | Phase | Priority | Effort | Dependencies | Owner | Status | Notes
AUTH-01 | Auth | Email magic-link login | As a contractor I want to log in with just my email so I don't manage passwords. | Magic link emailed; click signs in; link expires 15 min; rate limited per email/IP. | MVP | P0 | M |  | Brendan | Not Started | Auth.js + Resend
AUTH-02 | Auth | Single-user workspace | Each user gets an isolated workspace; data scoped by user_id. | All queries filter by session userId; Playwright test proves no cross-user read. | MVP | P0 | S | AUTH-01 | Brendan | Not Started | App-level scoping (RLS-lite); revisit when Phase 4 multi-user added.
PROJ-01 | Projects | Create/edit project | Create a project with name, status, dates. | CRUD endpoints + list view + edit form; soft-delete supported. | MVP | P0 | S | AUTH-02 | Brendan | Not Started
PROJ-02 | Projects | Client info per project | Capture client name, phone, email per project. | Stored on project; auto-populated into proposal PDF. | MVP | P0 | S | PROJ-01 | Brendan | Not Started
PROJ-03 | Projects | Site address + photos | Upload jobsite photos against a project for reference. | Multi-upload, thumbnails, delete, EXIF preserved. | MVP | P0 | M | PROJ-01 | Brendan | Not Started | Cloudflare R2 storage
EST-01 | Estimation | Sections / rooms | Group line items into rooms or scope sections. | Add / rename / delete / reorder sections per project. | MVP | P0 | S | PROJ-01 | Brendan | Not Started
EST-02 | Estimation | Line items | Add line items with qty, unit, labor hrs, labor rate, material $, markup %. | Inline-editable table; numeric validation; persists order_index. | MVP | P0 | M | EST-01 | Brendan | Not Started
EST-03 | Estimation | Calc engine | Pure calc: subtotals → labor burden → markup → overhead → profit → tax → total. | Vitest unit tests for every edge case (zero qty, 100% markup, rounding). | MVP | P0 | M | EST-02 | Brendan | Not Started | lib/calc.ts — single source of truth
EST-04 | Estimation | Duplicate item / section | One-click duplicate a line item or whole section. | Works at item and section level; preserves order. | MVP | P0 | S | EST-02 | Brendan | Not Started
EST-05 | Estimation | Reorder via drag | Drag-reorder items and sections. | Persists order_index to DB; works on touch. | MVP | P0 | S | EST-02 | Brendan | Not Started | dnd-kit
AI-01 | AI Capture | Voice → line items | Record voice memo of jobsite walk-through; AI proposes line items. | 60–120s clip → ≥1 mapped line item; flagged 'AI suggested' until confirmed. | MVP | P0 | L | EST-02, CAT-01 | Brendan | Not Started | Whisper → GPT-4o structured output; golden-set regression test.
AI-02 | AI Capture | Photo → line items | Take 1–10 photos; AI suggests line items based on visible scope. | Each suggestion shows confidence + source photo; user confirms each. | MVP | P0 | L | EST-02, CAT-01 | Brendan | Not Started | GPT-4o vision
AI-03 | AI Capture | Confirm UX (review-gate) | Every AI item must be confirmed before included in a proposal. | 'AI Suggested' badge until tap; cannot send proposal with unconfirmed items. | MVP | P0 | M | AI-01, AI-02 | Brendan | Not Started | UX-critical for trust + liability
AI-04 | AI Capture | Cost cap per project | Prevent runaway AI spend per project / per user. | Per-project token + $ cap; alert at 80%; hard block at 100%. | MVP | P0 | S | AI-01 | Brendan | Not Started
CAT-01 | Catalog | Seeded default catalog (~300 items, 6 trades) | Default library: carpentry, drywall, paint, electrical-rough, plumbing-rough, demo. | JSON seed loads on first signup; user can override defaults. | MVP | P0 | M |  | Brendan | Not Started | Curate from public sources for prototype.
CAT-02 | Catalog | Custom catalog items | Add / edit user-specific catalog items. | Per-workspace catalog table; full CRUD. | MVP | P0 | S | CAT-01 | Brendan | Not Started
CAT-03 | Catalog | Save project as template | Reuse a project's structure for the next similar bid. | Stored as JSON; instantiate into new project preserving sections + items. | MVP | P0 | M | EST-02 | Brendan | Not Started
MAT-01 | Materials | Material list per project | Auto-derive a consolidated shopping list from line items; editable; exportable as PDF. | Shows item, qty, unit, store hint, est cost; PDF export; shareable read-only link. | MVP | P0 | M | EST-02 | Brendan | Not Started | MOVED from Phase 2. Truck-day shopping use-case.
PROP-01 | Proposals | Proposal builder | Compose cover letter, scope narrative, exclusions, payment schedule, timeline. | Section editor with live preview; reorder; drafts auto-saved. | MVP | P0 | M | EST-03 | Brendan | Not Started
PROP-02 | Proposals | Branded PDF | PDF reflects contractor logo + brand color. | React PDF render; matches preview within 5%; A4 + Letter sizes. | MVP | P0 | M | PROP-01 | Brendan | Not Started | @react-pdf/renderer
PROP-03 | Proposals | Email proposal to client | Send PDF link via email to client. | Resend send; tracking pixel for 'viewed'; link to download PDF. | MVP | P0 | S | PROP-02 | Brendan | Not Started | MVP path: client signs paper or replies 'approved'. Hosted signing is Phase 2.
SIGN-01 | E-Sign | Hosted client signing page | Public token URL; client signs typed/drawn on canvas. | Mobile-friendly; canvas signature; prevents replay; expires. | Phase 2 | P1 | M | PROP-03 | Brendan | Not Started | MOVED from MVP per scope decision.
SIGN-02 | E-Sign | Audit log on signature | Capture IP, UA, timestamp, hash on every signature. | Immutable audit row; shown on proposal detail page. | Phase 2 | P1 | S | SIGN-01 | Brendan | Not Started
INFRA-01 | Infrastructure | Sentry + in-app feedback button | Centralized error monitoring + an in-app 'Send feedback' button → Slack/Discord webhook. | Errors captured with userId; feedback button on every screen. | Phase 2 | P1 | S |  | Brendan | Not Started | MOVED from MVP per scope decision.
MAT-02 | Materials | Supplier prices | Per-supplier price overrides for catalog items. | Supplier table + price-list; price chosen at PO time. | Phase 2 | P1 | M | MAT-01 | Brendan | Not Started
MAT-03 | Materials | PO PDF generation | Generate purchase order PDF for a supplier. | Filtered by supplier; PDF email-able; PO number sequence per workspace. | Phase 2 | P1 | M | MAT-02 | Brendan | Not Started
REC-01 | Receipts | Capture receipt photo / PDF | Snap or upload a paper receipt against a project. | Stored with thumbnail; supports HEIC/PNG/JPG/PDF. | Phase 2 | P1 | S | PROJ-01 | Brendan | Not Started
REC-02 | Receipts | Email-forward inbox for order confirmations | Forward order-confirmation emails (HD / Lowe's / Menard's / Ace / Amazon) to a unique inbox. | receipts+userid@app.com ingests; attachment + body stored against user. | Phase 2 | P1 | M |  | Brendan | Not Started | Postmark inbound or SendGrid Inbound Parse; SPF/DKIM verified.
REC-03 | Receipts | OCR + GPT-4o vision parse | Extract store, date, items, qty, unit price, tax, total from receipt or email. | ≥85% field accuracy on test set of 30 receipts; structured JSON output. | Phase 2 | P1 | L | REC-01, REC-02 | Brendan | Not Started
REC-04 | Receipts | Match receipt to project | User picks project; AI suggests based on date/amount/store. | Manual + AI-suggested match; one-click confirm. | Phase 2 | P1 | M | REC-03 | Brendan | Not Started
REC-05 | Receipts | Reconcile actual vs. estimated materials | Per line item, compare estimated vs. actual material spend. | Variance %, overrun flag, drill-down to receipt. | Phase 2 | P1 | M | REC-04, MAT-01 | Brendan | Not Started
REC-06 | Receipts | Export receipts by project | ZIP of all receipts + summary CSV for tax/job-costing. | Download endpoint; filterable by date range. | Phase 2 | P1 | S | REC-03 | Brendan | Not Started
SCHED-01 | Scheduling | Project calendar | Calendar view per project (day / week / month). | Drag-create events; recurring events supported. | Phase 2 | P1 | M | PROJ-01 | Brendan | Not Started
SCHED-02 | Scheduling | Sub assignments | Assign subcontractors to scheduled tasks. | Sub directory; assignment CRUD; conflict warnings. | Phase 2 | P1 | M | SCHED-01 | Brendan | Not Started
SCHED-03 | Scheduling | SMS / email reminders to subs | Notify subs day-before and morning-of an assignment. | Twilio + Resend; opt-out link; delivery status tracked. | Phase 2 | P1 | M | SCHED-02 | Brendan | Not Started
TIME-01 | Time | Crew clock-in / out | Mobile clock-in to a project for crew members. | GPS optional; manual entry fallback; geofence warning. | Phase 2 | P1 | M | PROJ-01 | Brendan | Not Started
TIME-02 | Time | Hours roll-up to project actuals | Compare estimated labor vs. actual hours per section. | Per-section variance dashboard. | Phase 2 | P1 | S | TIME-01, EST-02 | Brendan | Not Started
INV-01 | Invoicing | Convert proposal → invoice | Convert a signed proposal into an invoice. | Carries scope; editable; status tracking (draft/sent/paid). | Phase 2 | P1 | M | SIGN-01 | Brendan | Not Started
INV-02 | Invoicing | Progress billing (draws) | Configure draw schedule (deposit / mid / final). | Per-draw invoices; auto-suggest based on milestones. | Phase 2 | P1 | M | INV-01 | Brendan | Not Started
INV-03 | Invoicing | Payment link | Generic 'pay link' placeholder; payment recorded against invoice. | Manual mark-paid in Phase 2; Stripe integration deferred to Phase 4. | Phase 2 | P1 | M | INV-01 | Brendan | Not Started
CO-01 | Change Orders | Change order builder | Add scope/$ to a signed proposal mid-project. | Linked to original; new total; client must re-sign. | Phase 2 | P1 | M | PROP-01, SIGN-01 | Brendan | Not Started
CO-02 | Change Orders | Re-sign flow for change orders | Client re-signs change order via hosted page. | Reuses SIGN-01 flow; appended to audit log. | Phase 2 | P1 | S | CO-01, SIGN-01 | Brendan | Not Started
TAX-01 | 1099/Tax | Subcontractor profile + W-9 capture | Capture sub profile and W-9 PDF; encrypt EIN/SSN at rest. | pgcrypto encryption; access logged; W-9 PDF stored. | Phase 2 | P1 | M |  | Brendan | Not Started | PII handling — review with privacy/legal before go-live.
TAX-02 | 1099/Tax | Payment ledger by sub by year | Track all payments to each sub by tax year. | Per-sub annual total; filterable by year and project. | Phase 2 | P1 | M | TAX-01 | Brendan | Not Started
TAX-03 | 1099/Tax | Generate 1099-NEC PDF | Render IRS-aligned 1099-NEC PDF per sub (Copies B / C / 2). | Matches IRS form layout; spot-check against IRS sample. | Phase 2 | P1 | L | TAX-02 | Brendan | Not Started | Copy A requires IRS red-ink scannable form — direct user to e-file via IRS FIRE or Track1099 instead.
TAX-04 | 1099/Tax | Year-end bulk packet | ZIP of all subs' 1099s + summary CSV for the tax year. | One-click export; idempotent (regeneratable). | Phase 2 | P1 | S | TAX-03 | Brendan | Not Started
TAX-05 | 1099/Tax | 1096 transmittal generation | Generate IRS Form 1096 if user paper-files. | PDF; matches IRS form layout. | Phase 2 | P1 | S | TAX-03 | Brendan | Not Started
COMM-01 | Client | Client portal (view-only) | Client sees proposal, change orders, invoices in one URL. | Token-gated; no login required for client. | Phase 2 | P1 | M | PROP-03 | Brendan | Not Started
COMM-02 | Client | Comments on proposal sections | Client and contractor can thread comments per section. | Polling-based realtime OK; email notification on new comment. | Phase 2 | P1 | M | COMM-01 | Brendan | Not Started
VIZ-01 | Visualization | 3D room scan | Capture 3D geometry of an existing room. | LiDAR via WebXR on supported phones; 8–12 photo photogrammetry fallback; mesh stored. | Phase 3 | P2 | XL | PROJ-03 | Brendan | Not Started | Opt-in; LiDAR availability uneven on non-Pro iPhones.
VIZ-02 | Visualization | 3D viewer (web) | Render scanned room in proposal; client rotates / zooms. | three.js / react-three-fiber; loads <3s on mid-tier mobile. | Phase 3 | P2 | L | VIZ-01 | Brendan | Not Started
VIZ-03 | Visualization | Annotate 3D model with line items | Tag surfaces in the model with line items (this wall = drywall + paint). | Per-surface tag list; bidirectional link to estimate. | Phase 3 | P2 | L | VIZ-02, EST-02 | Brendan | Not Started
VIZ-04 | Visualization | Before-photo capture & alignment | Store original 'before' photos with camera pose for later alignment. | EXIF preserved; manual alignment helper in UI. | Phase 3 | P2 | M | PROJ-03 | Brendan | Not Started
VIZ-05 | Visualization | AI-generated 'after' photo | Generate a photorealistic 'after' image conditioned on before-photo + scope text. | Mandatory watermark 'AI-generated visualization, not a guarantee'; cap regenerations per proposal. | Phase 3 | P2 | XL | VIZ-04, EST-02 | Brendan | Not Started | Image-gen API cost ~$0.05–0.15/image; ToS disclaimer required.
VIZ-06 | Visualization | Side-by-side before / after slider | Drag-slider compare in proposal PDF + client view. | Touch swipe on mobile; static side-by-side fallback in PDF. | Phase 3 | P2 | M | VIZ-05 | Brendan | Not Started
QB-01 | Integration | QuickBooks Online sync | 2-way sync invoices, bills, customers with QBO. | OAuth flow; daily sync; conflict resolution. | Phase 4 | P3 | XL | INV-01 | Brendan | Not Started
MULTI-01 | Admin | Team roles (admin / foreman / sub) | Multi-user workspaces with role-based access control. | RBAC across all routes; invitation flow. | Phase 4 | P3 | L | AUTH-02 | Brendan | Not Started
LAUNCH-01 | Launch | Stripe billing | Subscription plans + checkout + customer portal. | Stripe Checkout; webhooks for plan changes. | Phase 4 | P3 | M |  | Brendan | Not Started
LAUNCH-02 | Launch | iOS App Store build | Capacitor wrapper of PWA; submit to App Store. | TestFlight beta; App Store review approved. | Phase 4 | P3 | L |  | Brendan | Not Started
LAUNCH-03 | Launch | Android Play Store build | Capacitor wrapper; submit to Play Store. | Internal track + production track approved. | Phase 4 | P3 | L |  | Brendan | Not Started
LAUNCH-04 | Launch | Marketing site | Public landing + pricing + features + signup CTA. | Next.js public route; SEO optimized. | Phase 4 | P3 | M |  | Brendan | Not Started
LAUNCH-05 | Launch | Help center / docs | Self-serve help docs and onboarding guides. | MDX or Notion-backed; searchable. | Phase 4 | P3 | M |  | Brendan | Not Started
LAUNCH-06 | Launch | Compliance hardening (SOC2-lite) | Audit log, data export, account deletion, encryption review. | Audit log endpoint, export endpoint, deletion job, encryption-at-rest verified. | Phase 4 | P3 | L |  | Brendan | Not Started
LAUNCH-07 | Launch | Multi-tenant security audit | Pen-test for row-level isolation across tenants. | External pen test report; remediation completed. | Phase 4 | P3 | M | MULTI-01 | Brendan | Not Started
LAUNCH-08 | Launch | Onboarding wizard | Self-serve guided first-project creation. | <3 min from signup to first estimate created. | Phase 4 | P3 | M |  | Brendan | Not Started
AGT-01 | Automation | Material-buying agent + delivery tracking | Autonomous agent purchases approved project materials from supported suppliers and tracks delivery status. | Reads MAT-01 list; user approves cart; agent places order via supplier API or email-cart; delivery status (ordered/shipped/delivered) updates project timeline; exception alerts on backorder. | Phase 4 | P3 | XL | MAT-01, MAT-02, REC-02 | Brendan | Not Started | Start with one supplier (Home Depot Pro) before generalizing. Requires user-stored payment + delivery address.
AGT-02 | Automation | Bid-send + follow-up agent | Autonomous agent sends proposals to clients and follows up on a configurable cadence until accepted/declined. | User approves send + cadence (e.g., D+3, D+7, D+14); agent emails follow-ups; stops on client reply, sign, or decline; weekly digest of open bids to contractor. | Phase 4 | P3 | L | PROP-03, SIGN-01 | Brendan | Not Started | Drafts must be human-approved before initial send; follow-ups can be auto-approved.
AGT-03 | Automation | Sub-estimate request agent | Autonomous agent reaches out to selected subcontractors for trade estimates (e.g., electrical, plumbing) on a project. | User picks trade + subs from directory; agent emails scope packet from estimate; collects responses (email or form); presents side-by-side comparison; nudges non-responders. | Phase 4 | P3 | L | SCHED-02, EST-02 | Brendan | Not Started | Sub directory is a precondition; consider rate-limit + opt-out per sub.
CAT-04 | Catalog | Shared catalog across users (backlog) | Optional: contributors share + improve a community catalog; per-user overrides preserved. | Opt-in; community items flagged; user can fork to private; contributor attribution. | Phase 4 | P3 | L | CAT-01, CAT-02 | Brendan | Not Started | Backlog item per scope decision: prototype stays isolated. Revisit only if friend feedback asks for it.

## A-Specific
A-Specific — Picklists & Constants
Phase | Priority | Status | Effort | Effort_Pts | Category
MVP | P0 | Not Started | S | 1 | Auth
Phase 2 | P1 | In Progress | M | 3 | Projects
Phase 3 | P2 | In Review | L | 7 | Estimation
Phase 4 | P3 | Done | XL | 12 | AI Capture
|  | Deferred |  |  | Catalog
Materials
Receipts
Proposals
E-Sign
Scheduling
Time
Invoicing
Change Orders
1099/Tax
Client
Visualization
Integration
Admin
Launch
Infrastructure
Automation

## Z-Validation-Checks
Z-Validation-Checks — Workbook Integrity
# | Check | Result | Detail
1 | All Feature_IDs are unique
2 | All Phase values are valid
3 | All Priority values are valid
4 | All Effort values are valid
5 | All Status values are valid
6 | Total feature count = 69
7 | MVP feature count = 21
8 | Phase 2 feature count = 28
9 | Phase 3 feature count = 6
10 | Phase 4 feature count = 14